## Bill of Services
SUMED
SUMMUM-EDIFICA JV
BILL OF SERVICES
Doc. No. / Version: | SUMED-BS-SPE-001-00
Date: | 31-Aug-20
Client: | Sociedad Portuaria Energética Multipropósito y Contenedores Puerto Solo Buenaventura, S.A. Nit 900739289-9
Contract: | Agreement as Project Management Consultant - PMC Services
PO No / Date: | SPE 20-006 / 10-Jul-2020
Scope: | Development of EPCICS Contract Schedules (various)
ITEM | DELIVERABLE | INVESTED MH | PRICE [COP$] | REMARKS
1 | Schedule 1 - Owner's Requirements | 60 | 11536123
2 | Schedule 3 - Bill of Quantities and Tax Breakdown | 11 | 2745195
3 | Schedule 4 - List of Contractor's Equipment | 32 | 7530600
4 | Schedule 6 - Contractual Time Schedule | 10 | 2737694
5 | Schedule 7 – Owner’s Permits | 8 | 1317736
6 | Schedule 8 – E&S Documents | 8 | 1317736
7 | Schedule 9 – Concession Agreement | 6 | 1960914
8 | Schedule 10 – Milestone Payment Schedule | 8 | 2857125
9 | Schedule 13 – Site | 14 | 3357258
10 | Schedule 14a – Tests on Completion | 20 | 7054020
11 | Schedule 14b – Tests after Completion | 8 | 2821608
12 | Schedule 15a – LNTP Works | 18 | 6455169
13 | Schedule 15b – Form of Limited Notice to Proceed | 15 | 5290515
14 | Schedule 17 – Interface Management | 57 | 19049973
15 | Schedule 18 – Owner’s Representative’s, LTA’s, Lenders’ E&S Adviser’s and Grantor’s Supervisor’s Duties and Responsibilities | 19 | 6020417
16 | Schedule 21 – Relied Upon Data | 18 | 4409166
17 | Schedule 22 – Day Work | 8 | 1843346
18 | Schedule 26 – Tender Data | 9 | 2678566
19 | Schedule 28 – Pre-Agreed Subcontractors | 7 | 1533736
20 | Schedule 29 – Designs and Drawings | 10 | 1647170
21 | Schedule 30 – Footprints | 20 | 6296434
22 | Schedule 32 – Critical Supply List | 12 | 4232412
23 | Schedule 34 – Form of Interface Agreement | 18 | 6490686
| SUBTOTAL | 396 | 111183599
| IVA (19%) | - | 21124883.81
| TOTAL | - | 132308482.81
NOTES:
1 | Prices are in Colombian Pesos (COP$).
2 | Manhours listed above correspond to reported progress as of 31/JUL/20.
3 | For a detailed price breakdown of invested manhours, please refer to "Exhibit 1".
By signing this document, the Client agrees to the services and conditions described herein.
| Andrés Rodríguez | Gene Lobrecht
| SUMED - Project Manager | Puerto Solo - Project Manager

## Exhibit 1
EXHIBIT 1 - SCHEDULES DEVELOPMENT ASSIGNMENT - MAN-HOURS BALANCE AS OF 31/JUL/20
ID | SCHEDULE | POWER ELECTRICAL MGR (ANDRES RODRIGUEZ) |  | PROJECT MANAGER (LUIS FERNANDO VESGA) |  | PORT MANAGER (ERIK GARRIDO) |  | GEOTECHNICAL SUPERVISOR (WILLIAM RUIZ) |  | CIVIL/STRUCTURAL SPEC. (MONIKA OLIVEROS) |  | MAN-HOURS |  | COST [COP] |  | PROGRESS (Note 1) | COMMENTS
|  | MH | RATE [COP] | MH | RATE [COP] | MH | RATE [COP] | MH | RATE [COP] | MH | RATE [COP] | BUDGET | INVESTED | BUDGET | INVESTED
1 | Schedule 1 - Owner's Requirements |  | 352701 | 3 | 388218 |  | 352701 | 25 | 204021 | 32 | 164717 | 45 | 60 | 15871545 | 11536123 | 85%
2 | Schedule 2 - [Reserved] | [15 empty] | Out of SUMED Scope of Work
3 | Schedule 3 - Bill of Quantities and Tax Breakdown |  | 352701 | 4 | 388218 |  | 352701 | 1 | 204021 | 6 | 164717 | 16 | 11 | 5643216 | 2745195 | 85%
4 | Schedule 4 - List of Contractor's Equipment |  | 352701 | 8 | 388218 |  | 352701 | 12 | 204021 | 12 | 164717 | 45 | 32 | 15871545 | 7530600 | 85%
5 | Schedule 5 - Contractor's Technical Specification |  | 352701 |  | 388218 |  | 352701 |  | 204021 |  | 164717 | 18 | 0 | 6348618 | 0
6 | Schedule 6 - Contractual Time Schedule |  | 352701 | 4 | 388218 |  | 352701 | 5 | 204021 | 1 | 164717 | 16 | 10 | 5643216 | 2737694 | 85%
7 | Schedule 7 – Owner’s Permits |  | 352701 |  | 388218 |  | 352701 |  | 204021 | 8 | 164717 | 8 | 8 | 2821608 | 1317736 | 85%
8 | Schedule 8 – E&S Documents |  | 352701 |  | 388218 |  | 352701 |  | 204021 | 8 | 164717 | 8 | 8 | 2821608 | 1317736 | 85%
9 | Schedule 9 – Concession Agreement |  | 352701 | 4 | 388218 |  | 352701 | 2 | 204021 |  | 164717 | 8 | 6 | 2821608 | 1960914 | 85%
10 | Schedule 10 – Milestone Payment Schedule | 2 | 352701 | 1 | 388218 | 5 | 352701 |  | 204021 |  | 164717 | 8 | 8 | 2821608 | 2857125 | 85%
11 | Schedule 11 – Form of Performance Letter of Credit | [15 empty] | Under Legal Attorney.
12 | Schedule 12 – Form of Notice to Proceed | [15 empty] | Out of SUMED Scope of Work
13 | Schedule 13 – Site |  | 352701 | 4 | 388218 |  | 352701 | 4 | 204021 | 6 | 164717 | 16 | 14 | 5643216 | 3357258 | 85%
14 | Schedule 14a – Tests on Completion |  | 352701 |  | 388218 | 20 | 352701 |  | 204021 |  | 164717 | 32 | 20 | 11286432 | 7054020 | 85%
15 | Schedule 14b – Tests after Completion |  | 352701 |  | 388218 | 8 | 352701 |  | 204021 |  | 164717 |  | 8 | 0 | 2821608 | 85% | Not considered in the initial Contract draft.
16 | Schedule 15a – LNTP Works | 7 | 352701 | 3 | 388218 | 8 | 352701 |  | 204021 |  | 164717 | 30 | 18 | 10581030 | 6455169 | 85%
17 | Schedule 15b – Form of Limited Notice to Proceed | 5 | 352701 |  | 388218 | 10 | 352701 |  | 204021 |  | 164717 |  | 15 | 0 | 5290515 | 85% | Not considered in the initial Contract draft.
18 | Schedule 16a – Owner’s Insurance | [15 empty] | Out of SUMED Scope of Work
19 | Schedule 16b – Contractor’s Insurance | [15 empty] | Out of SUMED Scope of Work
20 | Schedule 17 – Interface Management |  | 352701 | 8 | 388218 | 40 | 352701 | 9 | 204021 |  | 164717 | 100 | 57 | 35270100 | 19049973 | 85%
21 | Schedule 18 – Owner’s Representative’s, LTA’s, Lenders’ E&S Adviser’s and Grantor’s Supervisor’s Duties and Responsibilities |  | 352701 | 2 | 388218 | 13 | 352701 |  | 204021 | 4 | 164717 | 20 | 19 | 7054020 | 6020417 | 85%
22 | Schedule 19 – Form of Parent Company Guaranty | [15 empty] | Out of SUMED Scope of Work
23 | Schedule 20 – Direct Agreement | [15 empty] | Out of SUMED Scope of Work
24 | Schedule 21 – Relied Upon Data |  | 352701 | 4 | 388218 |  | 352701 | 14 | 204021 |  | 164717 | 20 | 18 | 7054020 | 4409166 | 85%
25 | Schedule 22 – Day Work |  | 352701 | 2 | 388218 |  | 352701 | 2 | 204021 | 4 | 164717 | 18 | 8 | 6348618 | 1843346 | 85%
26 | Schedule 23 – Form of Statement | [15 empty] | Out of SUMED Scope of Work
27 | Schedule 24 – Dispute Adjudication Board | [15 empty] | Out of SUMED Scope of Work
28 | Schedule 25 – Subcontractor Agreement Notice | [15 empty] | Out of SUMED Scope of Work
29 | Schedule 26 – Tender Data |  | 352701 | 5 | 388218 |  | 352701 | 2 | 204021 | 2 | 164717 | 18 | 9 | 6348618 | 2678566 | 85%
30 | Schedule 27 – Lenders’ Environmental and Social Requirements | [15 empty] | Out of SUMED Scope of Work
31 | Schedule 28 – Pre-Agreed Subcontractors |  | 352701 | 1 | 388218 |  | 352701 | 4 | 204021 | 2 | 164717 | 8 | 7 | 2821608 | 1533736 | 85%
32 | Schedule 29 – Designs and Drawings |  | 352701 |  | 388218 |  | 352701 |  | 204021 | 10 | 164717 | 8 | 10 | 2821608 | 1647170 | 85%
33 | Schedule 30 – Footprints |  | 352701 | 6 | 388218 | 8 | 352701 | 4 | 204021 | 2 | 164717 | 24 | 20 | 8464824 | 6296434 | 85%
34 | Schedule 31 – Form of Provisional Readiness Certificate | [15 empty] | Out of SUMED Scope of Work
35 | Schedule 32 – Critical Supply List |  | 352701 |  | 388218 | 12 | 352701 |  | 204021 |  | 164717 | 16 | 12 | 5643216 | 4232412 | 85%
36 | Schedule 33 – Indexation Formula | [15 empty] | Out of SUMED Scope of Work
37 | Schedule 34 – Form of Interface Agreement |  | 352701 | 4 | 388218 | 14 | 352701 |  | 204021 |  | 164717 | 18 | 18 | 6348618 | 6490686 | 85%
38 | Schedule 35 – Key Principles of Free Trade Zone Manual | [15 empty] | Out of SUMED Scope of Work
| TOTAL | 14 |  | 63 |  | 138 |  | 84 |  | 97 |  | 500 | 396 | 176350500 | 111183599
[13 empty] | 79.2% |  | 63.05%
NOTES:
1) In accordance with SUMED's Standard Quality Plan, reported progress is 85% since it is expected to receive comments/feedback from SEAONE. Deliverables will be at 100% progress when comments would be included.
2) Note that Schedules 14b and 15b were not included in the initial Contract draft.