## Bill of Services
SUMED
SUMMUM-EDIFICA JV
BILL OF SERVICES
Doc. No. / Version: | SUMED-BS-TPS-001-00
Period | July 21st to September 4th
Client / Nit: | Termo Puerto Solo SAS ESP Nit 901.149.278-1
Contract: | Agreement as Project Management Consultant - PMC Services
PO No / Date: | TPS 20-006 / 7-10-2020
Scope: | Support for the Termo Solo 2 Project
ITEM | DELIVERABLE | INVESTED MH | COP$/MH | PRICE [COP$] | REMARKS
1 | Weekly meeting preparation, attendance and report | 36 | 319661 | 11507796
2 | Engineering follow up Transmission Line (2 x week) | 14 | 319661 | 4475254
3 | Environmental permits follow up (2 x week) On Demand | 14 | 319661 | 4475254
4 | Righ of way adquisition and access follow up (2 x week) | 14 | 319661 | 4475254
5 | Contracts follow up (transmission lines, power plant, right of way, etc) (On demand) | 28 | 319661 | 8950508
6 | Work package information compilation (On demand) | 52 | 319661 | 16622372
7 | UPME, XM, CELSIA - EPSA, etc permits and connections (On demand). | 8 | 319661 | 2557288
8 | Environmental Project Description | 8 | 319661 | 2557288
9 | Interface management | 6 | 319661 | 1917966
10 | 0 | 0 | 319661 | 0
11 | 0 | 0 | 319661 | 0
| SUBTOTAL | 180 |  | 57538980
| IVA (19%) | - |  | 10932406.2
| TOTAL | - |  | 68471386.2
NOTES:
1 | Prices are in Colombian Pesos (COP$).
2 | Manhours listed above correspond to reported progress as of the time period listed above.
3 | For a detailed price breakdown of invested manhours, please refer to "Exhibit 1".
By signing this document, the Client agrees to the services and conditions described herein.
| Andrés Rodríguez | Gene Lobrecht
| SUMED - Project Manager | Puerto Solo - Project Manager

## Exhibit 1
EXHIBIT 1 - SCHEDULES DEVELOPMENT ASSIGNMENT - MAN-HOURS BALANCE AS FROM 21/JUL/20 TO 4/SEP/2020
ID | SCHEDULE | POWER ELECTRICAL MGR (ANDRES RODRIGUEZ) | [6 empty] | MAN-HOURS |  | COST [COP] |  |  | COMMENTS
|  | MH Jul 21st - 24th | MH Jul 27th - 31th | MH Aug 03rd - 07th | MH Aug 10th - 14th | MH Aug 17th - 21st | MH Aug 24th - 28st | MH Aug31st-Sep4th | BUDGET | INVESTED | RATE [COP] / HH | BUDGET | INVESTED
1 | Weekly meeting preparation, attendance and report | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 88 | 36 | 319661 | 28130168 | 11507796
2 | Engineering follow up Transmission Line (2 x week) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 44 | 14 | 319661 | 14065084 | 4475254
3 | Environmental permits follow up (2 x week) On Demand | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 44 | 14 | 319661 | 14065084 | 4475254
4 | Righ of way adquisition and access follow up (2 x week) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 44 | 14 | 319661 | 14065084 | 4475254
5 | Contracts follow up (transmission lines, power plant, right of way, etc) (On demand) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 88 | 28 | 319661 | 28130168 | 8950508
6 | Work package information compilation (On demand) | 4 | 4 | 10 | 12 | 14 | 4 | 4 | 88 | 52 | 319661 | 28130168 | 16622372
7 | UPME, XM, CELSIA - EPSA, etc permits and connections (On demand). |  |  |  | 2 | 2 | 2 | 2 | 88 | 8 | 319661 | 28130168 | 2557288
8 | Environmental Project Description | [5 empty] | 4 | 4 |  | 8 | 319661 | 0 | 2557288
9 | Interface management | [5 empty] | 4 | 2 |  | 6 | 319661 | 0 | 1917966
[10 empty] | 0 | 319661 | 0 | 0
[11 empty] | 319661 | 0 | 0
| TOTAL | 18 | 18 | 24 | 30 | 32 | 30 | 28 | 484 | 180 |  | 170707284 | 57538980
[10 empty] | 37.19% |  |  | 33.71%

## TS2 Bid
Termo Puerto Solo S.A.S. E.S.P.
| COP$/US$ | 3650
| COP$/HH | 319661
| TOTAL MH | 484
| TOTAL COP$ | 154715924
| TOTAL US$ | 42387.9244
TERMOSOLO 2 PROJECT
|  |  |  | 2 | 4 | 4 | 4 | 4 | 4
ID | Activities | MH |  | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | Total
1 | Weekly meeting preparation, attendance and report | 4 |  | 8 | 16 | 16 | 16 | 16 | 16 | 88
2 | Engineering follow up Transmission Line (2 x week) | 2 |  | 4 | 8 | 8 | 8 | 8 | 8 | 44
3 | Environmental permits follow up (2 x week) On Demand | 2 |  | 4 | 8 | 8 | 8 | 8 | 8 | 44
4 | Righ of way adquisition and access follow up (2 x week) | 2 |  | 4 | 8 | 8 | 8 | 8 | 8 | 44
5 | Contracts follow up (transmission lines, power plant, right of way, etc) (On demand) | 4 |  | 8 | 16 | 16 | 16 | 16 | 16 | 88
6 | Work package information compilation (On demand) | 4 |  | 8 | 16 | 16 | 16 | 16 | 16 | 88
7 | UPME, XM, CELSIA - EPSA, etc permits and connections (On demand). | 4 |  | 8 | 16 | 16 | 16 | 16 | 16 | 88
| Total Week | 22 |  | 44 | 88 | 88 | 88 | 88 | 88 | 484
| Up to Dec 2020 | MH/Month | W/M
1 | 2020-07-01 | 44 | 2
2 | 2020-08-01 | 88 | 4
3 | 2020-09-01 | 88 | 4
4 | 2020-10-01 | 88 | 4
5 | 2020-11-01 | 88 | 4
6 | 2020-12-01 | 88 | 4
| Total MH | 484
SUMED JV